## OVERVIEW
📊 DASHLY PROJECT OVERVIEW
PROJECT: | DASHLY - Dashboards for Everyone
DURATION: | 16 Weeks
GOAL: | Build & Launch Dashboard SaaS to Product Hunt
📋 QUICK ACCESS
→ BUILD Board | Track development tasks
→ MARKETING Board | Track marketing & growth
→ WEEKLY STANDUP | Weekly progress & metrics
✅ SETUP CHECKLIST
☐ Read DASHLY_STARTUP_CHECKLIST.txt (20 min)
☐ Register domain dashly.io
☐ Create Twitter @dashly
☐ Create GitHub org /dashly
☐ Create DASHLY logo (Canva)
☐ Subscribe to Claude Code ($20)
☐ Design database schema
☐ Deploy database to Railway
☐ Create Express + React projects
☐ Setup authentication system
⏱️ DAILY WORKFLOW
MORNING: Open BUILD board → Pick task → Move to "In Progress"
DURING DAY: Complete task → Move to "Testing" → Move to "Done"
FRIDAY: Standup → Update metrics → Plan next week

## BUILD Board
DASHLY - BUILD (My Tasks)
Backlog | This Week | In Progress | Testing | Done
MON: Design DASHLY Database Schema | Read DASHLY_STARTUP_CHECKLIST.txt
MON: Deploy Database to Railway | Register domain (dashly.io)
MON: Create Express Project | Create Twitter (@dashly)
MON: Create JWT Auth | Create GitHub org
TUE: Create Auth Middleware | Create DASHLY logo
TUE: Create Auth Routes | Subscribe Claude Code
TUE: Create Express Main Server
TUE: Test Auth System
WED: Create Vite + React Project
WED: Setup TailwindCSS
WED: Setup React Router
WED: Setup Zustand Store
THU: Create API Client
THU: Create Signup Page
THU: Create Login Page
THU: Create Protected Routes
FRI: Deploy Backend to Railway
FRI: Deploy Frontend to Vercel
FRI: Update Frontend API URL
FRI: Create Week 1 Documentation
FRI: Update Cowork Board

## MARKETING Board
DASHLY - MARKETING (My Marketing)
Backlog | This Week | In Progress | Scheduled | Posted
Write "Why We Built DASHLY" Blog Post | Register DASHLY Domain (dashly.io)
Create YouTube Launch Video | Create DASHLY Twitter Account
Design Social Media Graphics | Create Landing Page (Framer)
Write Product Hunt Launch Copy | Setup Email List (Mailchimp)
Setup Analytics (Plausible) | Create Twitter Content Calendar
Create Email Welcome Series
Plan Product Hunt Strategy
Prepare Launch Day Timeline

## WEEKLY STANDUP
DASHLY - WEEKLY STANDUP & PROGRESS
Week 1-4: Foundation | Week 5-8: Core Features | Week 9-12: Prep & Polish | Week 13: LAUNCH 🚀 | Week 14-16: Growth
✅ WHAT GOT DONE: • Database schema created • Express server running • React project setup • Auth system working • Backend deployed to Railway • Frontend deployed to Vercel 📊 METRICS: • Database tables: 10 • API endpoints: 5 • Pages created: 3 • Bugs fixed: 2 • Users: 1 (testing) 🚀 WHAT'S NEXT: Week 2: Auth pages + user profile Week 3: Dashboard CRUD Week 4: Query system 📌 BLOCKERS: None\! Foundation complete. 💪 STATUS: ✅ READY FOR WEEK 2